## Sheet1
Project Ecommerce
Progress Update Meeting - 23 September 2019
No. |  |  |  | Target Completion Date
Back End Page |  |  |  | Phase 1 (Before PB) | Phase 2 (After PB) | Phase 3 (30/10/19) | Phase 4 (15/11/19)
1 | Create back-end/admin user |  |  |  | x |  | x
2 | Page for viewing feedback |  |  | x |  | x
3 | Location
|  | - Cannot edit location description |  |  | x | x
|  | - Cannot insert multiple address |  |  | x | x
4 | Notification
|  | - New order |  |  | x |  | x
5 | Automatic approval setting (after specific duration)
6 | Mail template
|  | - User registration |  |  | x |  | x
|  | - Order approval |  |  | x |  | x
7 | Publish option on item |  |  |  | x |  | x
8 | Schedule post on item |  |  |  | x |  | x
9 | Link between e-commerce user and AME's customer
|  | - for new registration, AME's customer is automatically created |  |  | x |  | x
|  | - Issue for existing customer, client want to manually link |  |  | x |  | x
10 | No multiple UOM in e-commerce platform |  |  |  | x |  | x
11 | Shop information |  |  |  | x | x
Front End
1 | Shop information |  |  |  | x | x
2 | Location
|  | - Cannot edit location description |  | x |  | x
|  | - Cannot insert multiple address |  | x |  | x
3 | telephone number verification via SMS |  |  |  | x | x
4 | Notification |  |  |  | x |  | x
5 | Forget password |  |  |  | x | x
6 | Occupation on user registration form |  | Required by One-Eleven |  | x |  | x
7 | User profile image
|  | - upload |  |  | x |  | x
|  | - edit |  |  | x |  | x
8 | Order status
|  | -Edit Order Status | Order Status | x
|  | - Add received by customer | Pending |  | x | x
Approved
Cancelled
Shipping in progress
Driver has arrived
Received by customer
8 | Chat
ONE-ELEVEN
1 | Edit location description |  |  | x
2 | Occupation on customer registration form (Required) |  |  |  | x
3 | Auto-approval option on Sale Order |  |  |  | x
4 | Track all drivers' locations on Admin Ipad |  |  |  | x
5 | Telephone verification on user registration form (via SMS) |  |  |  | x
SKY KING
1 | Error when adding Symbol in description field |  |  | x |  |  | x
2 | Draft |  |  |  | x |  | x
3 | Publish |  |  |  | x |  | x
4 | Scheduled publish |  |  |  | x |  | x
5 | Web front-end layout - Static Change (Temporary) |  |  | x |  | x
6 | Web front-end layout - Dynamic with back-end |  |  |  | x |  | x
7 | Feedback on item in front end |  |  | x |  | x
8 | Feedback view in back end |  |  | x |  | x
RMS
1
2
3
DM Online Shop
1
2
3