## Sheet1
Project Ecommerce
Progress Update - 25 Oct 2019
Target Completion Date
No. |  |  | DONE | 2019-10-30 | 2019-11-15
Back End Page
1 | Create back-end/admin user |  |  |  | x
2 | Page for viewing feedback |  | x | x
3 | Location
|  | - Cannot edit location description |  | x
|  | - Cannot insert multiple address |  | x
4 | Notification
|  | - New order |  |  | x
5 | Automatic approval setting (after specific duration) |  | ?
6 | Mail template
|  | - User registration |  |  | x
|  | - Order approval |  |  | x
7 | Publish option on item |  |  |  | x
8 | Schedule post on item |  |  |  | x
9 | Link between e-commerce user and AME's customer
|  | - for new registration, AME's customer is automatically created |  |  | x
|  | - Issue for existing customer, client want to manually link |  |  | x
10 | No multiple UOM in e-commerce platform |  |  |  | x
11 | Shop information |  |  | x
Front End
1 | Shop information |  |  | x
2 | Location
|  | - Cannot edit location description |  | x
|  | - Cannot insert multiple address |  | x
3 | Telephone number verification via SMS |  |  | x
4 | Notification |  |  |  | x
5 | Forget password |  |  | x
6 | Occupation on user registration form |  |  |  | x
7 | User profile image
|  | - Upload |  |  | x
|  | - Edit |  |  | x
8 | Change label on order status |  | x
Order Status
Pending
Approved
Cancelled
Shipping in progress
Driver has arrived
Received by customer
9 | Chat
10 | Add product description / photo galaries (like DM app)
11 | User can save as picture
12 | Android - do not stretch picture (follow iOS pattern)
13 | Add Feature List
For each item, can choose which feature list to include
Feature List - can be automatic e.g. most popular, best selling, hot items, etc. or manual i.e. user may manually tick which feature list to be included
14 | Home Page
Can insert feature from feature list
Can add banner
Can add ads
Can add video
15 | Product List under Category
Grid set up for listing item in Product Category
16 | Product list under Home
Grid set up
17 | Menu Bar
Add Promotion/News Tab
18 | Overall
Theme color - can be changed
ONE-ELEVEN
1 | Edit location description
2 | Occupation on customer registration form (Required)
3 | Auto-approval option on Sale Order
4 | Track all drivers' locations on Admin Ipad
5 | Telephone verification on user registration form (via SMS)
SKY KING
1 | Error when adding Symbol in description field |  |  |  | x
2 | Draft |  |  |  | x
3 | Publish |  |  |  | x
4 | Scheduled publish |  |  |  | x
5 | Web front-end layout - Static Change (Temporary) |  |  | x
6 | Web front-end layout - Dynamic with back-end |  |  |  | x
7 | Feedback on item in front end |  |  | x
8 | Feedback view in back end |  |  | x